## PRODUCT BACKLOG
Product Backlog ID | Priority (M/S/C/W) | User Process ID | user process | Complexity | Risk/ Impact(L-Low, M- Medium, H-High) | Type | Comments
1 | M | Up:1 | Create an account | Very Simple | M | Functional
2 | M | Up:2 | User should have a unque identification code | Complex | H | Functional
3 | M | Up:3 | login to the account | Very Simple | M | Technical
4 | M | Up:4 | Check for available flights | Very Simple | M | Technical
5 | M | Up:5 | Book flights | Very Simple | H | Technical
6 | C | Up:6 | Ticket options as business, economy, first class. | Average | L | Technical
7 | M | Up:7 | User can view the booking status | Very Simple | M | Technical
8 | S | Up:8 | User can cancel the booking if needed | Average | H | Technical
9 | S | Up:9 | User can edit their profile | Average | L | Technical
10 | C | Up:10 | User can delete their account | Very Simple | L | Technical
11 | M | Up: 11 | Admin can login | Complex | H | Functional
12 | M | Up: 12 | Admin can add information | Complex | L | Technical
13 | M | Up: 13 | Admin can view available information | Average | L | Technical
14 | M | Up: 14 | Admin can cancel or modify flight, schedule flights and route details | Average | L | Technical
15 | M | Up:15 | Authentication of the User(Valid/Invalid User) | Average | L | Functional
16 | S | Up: 16 | Admn can view user | Very Simple | L | Technical
17 | M | Up:17 | Admin can edit/modify User | Average | M | Functional
18 | S | Up: 18 | Admin can delete existing user | Very Simple | L | Technical
19 | S | Up: 19 | Admin can update Airport Details | Very Simple | L | Technical
20 | W | Up: 20 | The application does not cover boarding pass generation and seating plans. | Very Simple | L | Non-Functional
21 | W | Up: 21 | Third party applications like email & sms integrations. | Very Simple | L | Non-Functional
22 | W | Up: 22 | Payments are not yet accepted by the application | Very Simple | L | Non-Functional
23 | W | Up: 23 | Customers are not able to do Web Check-In | Very Simple | L | Non-Functional
24 | W | Up: 24 | Customers cannot check their Flight Status | Very Simple | L | Non-Functional
25 | M | Up: 25 | Session Timeout(if no activity) | Average | M | Technical
26 | C | Up: 26 | Chatbot | Complex | M | Functional
27 | W | Up: 27 | User can Logout | Average | H | Technical